## Excess Surrender Statement (hidden)
Home Sector ADP 2015-16
ADP/Code # | Sub- Sector | Project Name | Local Cost | Foreign Cost | Date of Commt. | Date of Completion | Total Cost | Exp. till 30th June 2014 | Local Alloc. | Foreign Allocation | Total Allocation | Alloc. | Rev. Alloc. | Rel. | Foreign Release | Exp. in CFY 2015-16 | Foreign Expenditure | Re-appr opriation | Excess | Surr. | Exp. till 30th June 2015. | Savings/ Surr. | (%) Against Rev. Alloc. | Physical Progress/ Remarks | Remarks
Ongoing Schemes HTA's Sector
585/140150 | HTA | Safe City Project Peshawar (PC-II Approved) | 1500 | 0 | .. | .. | 1500 | 0 | 250 | 0 | 250 | 250 | 90.257 | 90.257 | 0 | 0 | 0 | 34.743 | 0 | 34.743 | 0 | 0 | 0% | Agreement signed on 20.03.2015.PC-I/DCE's submitted to Home deptt. A committee has been notified to check all the parameters of the PC-I. Observations raised by the committee shared with NADARA. reply awaited.
586/120685 | HTA | Strengthening Rule of Law in Malakand (SRLM) (UNDP Assisted) | 534.75 | 1004 | 2013-07-01 | 30.06.2015 | 1538.75 | 187.96 | 0.001 | 219.218 | 219.219 | 0.001 | 0.005 | 0.005 | 0 | 0 | 0 | 0 | 0 | 0 | 334.75 | 0 | 0% | Refurbishment of court houses, Training for Proscutors, Establishment of operationilze Data Centre in the operations room of CPO Peshawar, Establishement of Forensic Science Laboratory (FSL) in Swat, Establishement of Regional Training centre at Swat.
587/110515 | HTA | Automation of Home Department | 105 | 0 |  | 30.06.2015 | 105 | 47.007 | 20 | 0 | 20 | 20 | 38.857 | 38.857 | 0 | 30 | 0 | 0 | 18.857 | 0 | 61.557 | 0 | 77.21% | Prosecution Management Information System, Major Head salary. Salary based Project and Agreement renewed,the PC-I is in the revision process to meet the liabilities of current financial year. Revised PC-I approved amounting to Rs. 100.714 (million) in the PDWP meeting held on 17.11.2015.
588/120797 | HTA | Strengthening of Prosecution Directorate, PCMC and Planning Cell at Home Department. | 140.764 | 0 | 02.10.2014 | 30.06.2017 | 140.764 | 42.34 | 35 | 0 | 35 | 35 | 17.5 | 17.5 | 0 | 13.66 | 0 | 0 | 0 | 0 | 62.34 | 0 | 78.06% | Technical Evaluation of equipments and recruitment under process.
589/120901 | HTA | Impact Assessment / Validation of De-Radicalized Emancipation Program. | 291.74 | 0 | .. | 30.06.2016 | 291.74 | 250.841 | 8.8 | 0 | 8.8 | 8.8 | 6.6 | 6.6 | 0 | 1.796 | 0 | 0 | 0 | 0 | 282.984 | 0 | 27.21% | After June 2015 the Project will be executed by Home deptt. Currently the Project is going smoothly. 1241 No.s of beneficiaries got benefited through the siad program in Swat.
590/130561 | HTA | Strengthening Rule of Law for Citizens Justice and peace in KPK through UNDP (EU Assisted). | 0.001 | 1086.47 | .. | .. | 1086.471 | 0 | 0.001 | 387.637 | 387.638 | 0.001 | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Financial Agreement signed b/w European Union & Economic Affairs Division Pakistan. Contract Agreement with UNDP signed on 31.12.2014. Funded by European Union and will be executed by UNDP. The Project is not yet initiated.
591/130562 | HTA | Peace Building initiative for Khyber Pakhtunkhwa Project (DFID). | 0.001 | 4802 | 01.08.2013 | 31.12.2016 | 4802.001 | 0 | 0.001 | 1072 | 1072.001 | 0.001 | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Model Police station, community policing, correctional services, strengthening police investigation capacity, Re-draft investigation chapter of police rules 1934, pre and in- service training for Police , prosecutors, prison and probation officers. The program will be extended to 4 other districts ie Nowshera, Charssada, Mardan & Swabi.
592/140157 | HTA | Strengthening of the Directorate of Reclamation & Probation in Khyber Pakhtunkhwa. | 16.291 | 0 | 01.07.2014 | 30.06.2016 | 16.291 | 0 | 6.291 | 0 | 6.291 | 6.291 | 4.717 | 4.717 | 0 | 1.5 | 0 | 0 | 0 | 0 | 3.247 | 0 | 31.8% | Tenders Evaluation of Equipments under process. Recruitment under process.
593/140563 | HTA | De-Radicalization Program for Khyber Pakhtunkhwa. | 59.464 | 0 | 01.07.2014 | 30.06.2017 | 59.464 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | Scheme Dropped
New Schemes HTA's Sector
594/150262 | HTA | Strengthening of the Directorate of Provincial Public Safety & Police Complaints Commssion and its District formations. | 60 | 0 | .. | .. | 60 | 0 | 10 | 0 | 10 | 10 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | PC-I approved in the DDWP meetig held on 03.11.2015.
595/150768 | HTA | Technical Assitance for Implementation of Citizens Justice and Peace Programme in Khyber Pakhtunhwa (EU Assisted). | 0.001 | 457.461 | .. | .. | 457.462 |  | 0.001 | 155.76 | 155.761 | 0.001 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | The total Budget of Citizen Justice & Peace Program is € 3.8 Million. The project is in the inception phase.
596/150769 | HTA | Pakistan's action to Counter Terrorism (PACT) with special reference to Khyber Pakhtunkhwa through UNODC (EU Assisted). | 0.001 | 801.71 | .. | .. | 801.711 | 0 | 0.001 | 251.966 | 251.967 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | The project is in the inception phase. MOU not yet signed.
Total | [6 empty] | 10859.654 | 528.148 | 350.096 | 2086.581 | 2436.677 | 350.096 | 160.438 | 160.438 | 0 | 46.956 | 0 | 44.743 | 18.857 | 44.743 | 744.878 | 0 | 29.27%
Ongoing Schemes Police Sector
597/110359 | Police | 23 Secure armories across province and Mini Police line Hangu (P.M Package, 2nd and 3rd Tranch) | 588.93 | 0 | 07.06.2013 | .. | 588.93 | 240 | 158.93 | 0 | 158.93 | 158.93 | 119.197 | 119.197 | 0 | 36.456 | 0 | 0 | 0 | 0 | 430 | 0 | 30.58% | 12 Units completed & work on 06 units substantially completed. Mini P.L 60% completed.
598/130418 | Police | Construction of Instructor's Hostel at Police Training Center, District Hangu. | 30 | 0 |  |  | 30 | 0 | 29.832 | 0 | 29.832 | 29.832 | 22.374 | 22.374 | 0 | 0.126 | 0 | 0 | 0 | 0 | 0.168 | 0 | 0.5632% | Site clear. Excavation & foundatioin in progress
599/20602 | Police | Construction of Central Police Office in Peshawar. | 553.125 | 0 |  |  | 553.125 | 254.086 | 60.039 | 0 | 60.039 | 60.039 | 45.0285 | 45.0285 | 0 | 0.964 | 0 | 0 | 0 | 0 | 335.171 | 0 | 2.141% | Structure work of Package-II completed. OHT in progress.Final touches in progress. Summary for 3rd Revision in process at P&D department.
600/140264 | Police | F/S & Strengthening of Security Crescent Around Peshawar. (INL Assisted) | 200 | 800 |  |  | 1000 | 0 | 99 | 400 | 499 | 99 | 49.5 | 49.5 | 0 | 24.6 | 0 | 0 | 0 | 0 | 24.6 | 0 | 49.7% | tendering process of 31 units completed. Acceptance is awaited from INL islamabad.
601/140265 | Police | F/S & Construction of School of Investigation and Intelligence for Khyber Pakhtunkhwa. (PC-II Approved on 25.09.2014) | 100 | 0 |  |  | 100 | 0 | 40 | 0 | 40 | 40 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | site scope initiated on 16.11.2015. Pre PDWP held on 15.01.2016. it was decided to split the scheme in phase I-II
602/140263 | Police | F/S & Construction of Headquarters for Counter Terrorism Department at District Nowshera. (PC-II Approved on 25.09.2014) | 120 | 0 |  |  | 120 | 0 | 53.578 | 0 | 53.578 | 53.578 | 26.788 | 26.788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | PC-I submitted to P&D dept. pre PDWP held on 15.01.2016. it was decided to split the scheme in phase I-II
603/130587 | Police | Construction of Police Lines Daggar, District Buner (INL Assisted) | 0.002 | 799.595 |  |  | 799.597 | 0 | 0.001 | 300 | 300.001 | 0.001 | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | work in full swing on varioius building of the scheme.
604/140836 | Police | Construction of Police stations at Kotkai Khazana and Re-construction of Police Check Posts at Miskini and Kambat Dir Lower. (PC-II Approved on 25.09.2014) | 70 | 0 |  |  | 70 | 0 | 40 | 0 | 40 | 40 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | scheme approved by PDWP, summary approved by CM on 26.01.2016 regarding change of site from kotkai khazana to Asbanr.
605/80599 | Police | Project Coordination Unit for Implementation of Law & Order initiatives in Khyber Pakhtunkhwa. | 276.203 | 0 | 25.08.08 | 31.12.16 | 276.203 | 177.912 | 46.125 | 0 | 46.125 | 46.125 | 34.593 | 34.593 | 0 | 29.655 | 0 | 0 | 0 | 0 | 230.078 | 0 | 85.73% | In progress. Major Head salary.
606/100447 | Police | Special Development Support for Khyber Pakhtunkhwa Police. (SDSP Phase-II) | 2400 | 0 | 21.02.11 | beyond 2014-15 | 2400 | 1700 | 60 | 0 | 60 | 60 | 45 | 45 | 0 | 28.885 | 0 | 0 | 0 | 0 | 2340 | 0 | 64.19% | 05 NO's Unit completed & 04 units substantially completed & 04 units in final stage
607/120248 | Police | Special Development Support for Khyber Pakhtunkhwa Police (Tor Ghar = Rs. 400.00 M) (SDSP Phase-III) | 2000 | 0 | 2013-14 | 2015-16 | 2000 | 44 | 390 | 0 | 390 | 390 | 200 | 200 | 0 | 199.98 | 0 | 0 | 0 | 0 | 469.8 | 0 | 99.99% | i. Court stay vacated at P.L-II Mardan. ii. Work in progress on 06 units in progress. iii. 01 units completed. iv. 03 units land issue.
608/120885 | Police | Establishment of Offices for Special Branch Police, Khyber Pakhtunkhwa. | 115.067 | 0 | 01.03.14 | 2014-15 | 115.067 | 20 | 20 | 0 | 20 | 20 | 15 | 15 | 0 | 11.961 | 0 | 0 | 0 | 0 | 95.067 | 0 | 79.74% | work on 01 unit completed and 04 in progress. i. Mardan ii. Kohat iii. Abbottabad iv. DI Khan
609/130378 | Police | Special Development Support for Khyber Pakhtunkhwa Police. (SDSP-IV) | 1048 | 0 |  |  | 1048 | 0 | 350 | 0 | 350 | 350 | 175 | 175 | 0 | 73.939 | 0 | 0 | 0 | 0 | 73.939 | 0 | 42.25% | Work on 07 Units in progrtess. Court stay issued on P.L Timergara Dir-Lower. Police Lines: 03 Police Stations: 03 Police Posts: 02
610/140124 | Police | Special Development Support for Khyber Pakhtunkhwa Police and creation of Model Police Stations (SDSP-V) | 500 | 0 |  |  | 500 | 0 | 230.567 | 0 | 230.567 | 230.567 | 115.282 | 115.282 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0% | PC-I approved by PDWP 10.02.2016.
611/140807 | Police | F/S and Development of Police Infrastructure in Khyber Pakhtunkhwa (Police Station Kabalgram, Chauga, Olandar, Dandai District Shangla, Swari at District Buner, Gawaleriand Gat- Poechar at district Swat, Kuz Paro District Kohistan (CM Directive) (PC-II Approved on 25.09.2014) | 300 | 0 |  |  | 300 | 0 | 75 | 0 | 75 | 75 | 37.5 | 37.5 | 0 | 2.818 | 0 | 0 | 0 | 0 | 2.818 | 0 | 7.515% | AA issued on 29.12.2015. work in progress.
New Schemes Police Sector
612/150636 | Police | Construction of Watch Towers in cantonment & rural Division for Enhanced security in Funnel Area of Bacha Khan International Airport Peshawar. | 160 | 0 |  |  | 160 | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PC-I approved on 10.02.2016.
613/151081 | Police | Construction of Traffic Warden Headquarters at Peshawar. | 100 | 0 |  |  | 100 | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PC-II for Consultants Hiring approved conditionally due to non availability of land.
614/110557 | Police | Additional Works in Joint Police Training Center at Nowshera. (INL Assisted) | 0.001 | 92.2 | 05.07.2011 | 05.07.2013 | 92.201 | 0 | 0.001 | 92.2 | 92.201 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tendering process is in progress.
615/140257 | Police | Enhancing & Strengthening the capacity of Bomb Disposal Unit of Police Department in Khyber Pakhtunkhwa. (Presentation to PDWP) | 275 | 0 |  |  | 275 | 0 | 30 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I.G (Police) no response
616/150637 | Police | Non-Intrusive X-Rays Vehicle Inspection System (NVIS), Scanners. | 50 | 0 |  |  | 50 | 0 | 50 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 No. Sites selected at Kohat Road & Kacha Garhi Peshawar. Scope of work awaited.
Total | [6 empty] | 10578.123 | 2435.998 | 1753.073 | 792.2 | 2545.273 | 1753.073 | 925.2635 | 925.2635 | 0 | 409.384 | 0 | 0 | 0 | 0 | 4051.641 | 0 | 44.25%
Ongoing Schemes Prisons Sector
617/30758 | Prison | F/S & Construction of Central Prison D.I.Khan on Existing site. | 476.098 | 0 | 30.09.2010 | 30.06.2015 | 476.098 | 316.826 | 31.772 | 0 | 31.772 | 31.772 | 31.772 | 31.772 | 0 | 15.886 | 0 | 0 | 15.886 | 0 | 359.326 | 0 | 50% | Pack-I: (04) Guard Room, (02) middle school finishing in progress. Pack-2: (08) Cat-III, (35) Cat-VI residences in progress. Pack-3: (06) Single ward Barrack/mess and Residences in progress.
618/140137 | Prison | F/S & Construction of Sub Jail Banda Daud Shah, Karak. (PC-II Approved on 27.08.2014) | 150 | 0 | .. | .. | 150 | 0 | 35 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.5 | #DIV/0! | Scheme Dropped.
619/80466 | Prison | Construction of District Jail Hangu (Phase- I) 50/50 Cost sharing Basis with FATA. (Provincial Funds exhausted. Remainig funds to be released by FATA) | 264.391 | 0 | 24.06.2009 | 30.06.2015 | 264.391 | 178.606 | 0.001 | 0 | 0.001 | 0.001 | 0.001 | 0.001 | 0 | 0 | 0 | 0 | 0 | 0 | 178.606 | 0 | 0% | Barracks are in the finishing stage. Admin Block damaged due to bomb blast. Mosque finishing stage laid. Development work in progress. Provincial share had been utilized. 68% of work completed. Admin Block, water Tank, Barracks, Hospital. FATA has to utilize & release the remaining 50% share.
620/20889 | Prison | F/S, Planning, Designing & Construction of Central Prison, Peshawar (Phase-I). | 1408.46 | 0 | 01.05.2012 | 30.06.2015 | 1408.46 | 151.97 | 200 | 0 | 200 | 200 | 189.317 | 189.317 | 0 | 189.317 | 0 | 0 | 89.317 | 0 | 382.67 | 0 | 100% | 02 Isolation Cells, 06 Barracks parameters, Segregation wall completed. Design of sub structure reviewed by M/S NESPAK.
621/140144 | Prison | F/S & Construction of District Jail Nowshera. (PC-II Approved on 27.08.2014) | 150 | 0 | .. | .. | 150 | 0 | 35 | 0 | 35 | 35 | 17.5 | 17.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | PC-II amounting to Rs. 7.500 (M) Approved in the DDWP meeting held on 27.08.2014. A.A issued on 17.09.2014. (LOA issued to A.I.D consultant on 22.01.2015) Master Planning by consultant in progress.
622/120189 | Prison | Construction of District Jail Swabi (Phase-II) (PC-II Approved on 26.11.2013) | 500 | 0 | .. | .. | 500 | 0 | 35 | 0 | 35 | 35 | 17.5 | 17.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Technical Evlauation of 2nd RFP in progress. PC-II amounting to Rs. 25.00 (M) approved on 26-11-13. PC-I/Detailed Cost Estimates not yet prepared by SAMPAK Lahore. LOA issued on 31.01.2014. PC-I pending. SAMPAK blacklisted. Master plan & Design discussed with I.G (Prison) amendments made. 2nd time RFP floated.
623/140132 | Prison | Re-Construction of District Jail Swat (PC-II Approved) | 150 | 0 | .. | .. | 150 | 0 | 60 | 0 | 60 | 60 | 15.683 | 15.683 | 0 | 0.682 | 0 | 14.317 | 0 | 14.317 | 0.682 | 0 | 4.349% | PDWP held on 09.02.2016 in which PC-I/DCE's amounting to Rs. 821.938 (Million) was deferred. PC-II amounting to Rs. 6.51 (M) approved in the PDWP meeting on 10.05.14. (S.E Solution consultant selected for preparation of PC-I/ DCE’s).
624/140138 | Prison | F/S & Construction of Sub Jail Nathiagali, Abbottabad. (PC-II Approved on 27.08.2014) | 150 | 0 | .. | .. | 150 | 0 | 25 | 0 | 25 | 25 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Master Planning under Progress. PC-II amounting to Rs. 7.500 (M) Approved in the DDWP meeting held on 27.08.2014. A.A issued on 17.09.2014. (Nespak selected as consultant for preparation of PC-I/DCE’s. Agreement signed on 04.04.2015.).
625/100065 | Prison | Construction of Hostel for Trainees at Central Prison Haripur. | 200.08 | 0 | 10.11.2012 | 30.06.2015 | 200.08 | 0.44 | 80 | 0 | 80 | 80 | 40 | 40 | 0 | 35 | 0 | 0 | 0 | 0 | 52.169 | 0 | 87.5% | First Floor construction in progress.
626/100456 | Prison | Construction of High Security Zones in 06 Jails, Khyber Pakhtunkhwa. | 221.79 | 0 | 15.04.2011 | 30.06.2015 | 221.79 | 112.41 | 50 | 0 | 50 | 50 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 122.322 | 0 | 0% | Revised PC-I amounting to Rs. 227.570 (M) approved in the PDWP meetinh held on 21.01.2016. A.A issued on 12.02.2016.
627/110131 | Prison | Improvement of Existing Jails in Khyber Pakhtunkhwa. | 210.24 | 0 | 24.03.2012 | 30.06.2015 | 210.24 | 137.651 | 64.7 | 0 | 64.7 | 64.7 | 16.175 | 16.175 | 0 | 0 | 0 | 0 | 0 | 0 | 144.237 | 0 | 0% | Revised PC-I amounting to Rs. 424.275 (M) submitted to P&D department on 09.12.2015. Pre-PDWP held on 08.03.2016.
628/110455 | Prison | Construction / improvement of Judicial Lockups (Bakhshi Khanas) in Khyber Pakhtunkhwa. | 205 | 0 | 07.05.2012 | 30.06.2014 | 205 | 129.625 | 52.359 | 0 | 52.359 | 52.359 | 13.089 | 13.089 | 0 | 0 | 0 | 0 | 0 | 0 | 131.076 | 0 | 0% | Revised PC-I amounting to Rs. 171.000 (M) submitted to I.G (Prisons), but was returned without signature.
629/120799 | Prison | Enhancing Security of Jails in Khyber Pakhtunkhwa. | 765 | 0 | 03.06.2013 | 30.06.2016 | 765 | 162.361 | 150 | 0 | 150 | 150 | 10 | 10 | 0 | 0 | 0 | 65 | 0 | 65 | 424.499 | 0 | 0% | Technical Evaluation & proposal presentation of Security Equipments under process.
630/120802 | Prison | Execution of Additional Work at Central Prison Haripur and Sub Jail Karak. | 143 | 0 | 02.04.2013 | 30.06.2015 | 143 | 0 | 143 | 0 | 143 | 143 | 35.75 | 35.75 | 0 | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 41.96% | Revised PC-I amounting to Rs. 191.540 (M) approved in the DPWP meeting held on 08.10.2015. A.A issued on 05.11.2015. Haripur: Rs. 147.263 (M) Karak: Rs. 44.277 (M) Scope of work includes remaining boundry wall, interview sheds, watch towers & Allied facilities etc. Tenders invited.
631/130281 | Prison | Solar Energization of various Jails in Khyber Pakhtunkhwa (Except Central Prsion Haripur) (PC-II Approved on 20.02.2014) | 300 | 0 | .. | .. | 300 | 0 | 99.999 | 0 | 99.999 | 99.999 | 49.998 | 49.998 | 0 | 0 | 0 | 0 | 0 | 0 | 5.799 | 0 | 0% | PC-I amounting to Rs. 367.069 (Million) approved in the PDWP meeting held on 21.01.2016. A.A issued on 12.02.2016.
632/140205 | Prison | F/S & Construction of Admin Blocks and Barracks for Prison Security Force (Watch & ward Staff) in Khyber Pakhtunkhwa. (PC-II Approved on 26.11.2014) | 250 | 0 | .. | .. | 250 | 0 | 30 | 0 | 30 | 30 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | PC-I/DEC’s amounting to Rs. 487.320 (M) submitted to P&D department on 27.04.2016.
New Schemes Prisons Sector
633/150272 | Prison | Feasibility Study and Construction of Central Prison D.I.Khan on existing site (Phase-II). | 400 | 0 | .. | .. | 400 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PC-I/DEC’s amounting to Rs. 812.996 (M) approved in the PDWP meeting held on 28.03.2016. A.A issued on 05.04.2016.
634/150278 | Prison | Feasibilty Study for Construction of District Jail Malakand. | 10 | 0 |  |  | 10 |  | 10 | 0 | 10 | 10 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Site Selection under process.
635/150638 | Prison | F/S for Construction of Judicial Lockup in Shangla. | 5 | 0 |  |  | 5 |  | 5 | 0 | 5 | 5 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Site Selection under process.
636/140148 | Prison | Provision of Electricity through separate Feeders to Central Prisons in Khyber Pakhtunkhwa. | 200 | 0 |  |  | 200 |  | 100 | 0 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Case with WAPDA (PESCO) for installation of separate feeders to 04 Central Prisons in process. (Estimate to be taken by I.G (Prisons) from WAPDA (PESCO).
637/150267 | Prison | Improvement/ Strengthening of Female and Juvenile Sections in all the Prisons of Khyber Pakhtunkhwa. | 60 | 0 |  |  | 60 |  | 30 | 0 | 30 | 30 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | PC-I/DEC’s amounting to Rs. 251.501 (M) submitted to P&D department on 04.04.2016.
638/150277 | Prison | Construction of One Barrack in Selected Jails of Khyber Pakhtunkhwa for Security Personnel. | 50 | 0 |  |  | 50 |  | 20 | 0 | 20 | 20 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | PC-I/DCE’s under preparation. S.E Peshawar nominated as focal person. Not yet prepared.
639/150281 | Prison | Capacity Building of Satff in Various Jails of Khyber Pakhtunkhwa. | 100 | 0 |  |  | 100 |  | 25 | 0 | 25 | 25 | 6.25 | 6.25 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | PC-I amounting to Rs. 57.000 (m) approved in the DDWP meeting held on 30.12.2015. A.A issued on 31.12.2015.
640/150282 | Prison | Construction/Improvement of messing facilities for staff & Prisoners in the Jails of Khyber Pakhtunkhwa. | 50 | 0 |  |  | 50 |  | 25 | 0 | 25 | 25 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | PC-I/DEC’s amounting to Rs. 59.999 (M) submitted to Home department on 01.03.2016 and will not be forwarded to the competemt forum of DDWP till further orders from P&D about frozen of unapproved schemes in CFY 2015-16.
641/150283 | Prison | Video Conferencing & Video Linking Facilites in Internemnt Centres and Anti-Terrorism Courts alongwith all the Jails of Khyber Pakhrunkhwa. | 60 | 0 |  |  | 60 |  | 30 | 0 | 30 | 30 | 7.5 | 7.5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | PC-I amounting to Rs. 34.878 (m) approved in the PDWP meeting on 16.07.2015.
642/150579 | Prison | Provision of Water Filteration Plants in remaining Jails in Khyber Pakhtunkhwa. (Phase-II) | 40 | 0 | .. | .. | 40 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Case taken up by I.G (Prisons) with PHE department for preparation of PC-I/DCE’s.
Total | [6 empty] | 6519.059 | 1189.889 | 1396.831 | 0 | 1396.831 | 1396.831 | 490.535 | 490.535 | 0 | 255.885 | 0 | 79.317 | 105.203 | 79.317 | 1816.386 | 17.5 | 52.1645 | % Against Allocation | % Against Rev. Alloc.
G.Total | [6 empty] | 27956.836 | 4154.035 | 3500 | 2878.781 | 6378.781 | 3500 | 1576.2365 | 1576.2365 | 0 | 712.225 | 0 | 124.06 | 124.06 | 124.06 | 6612.905 | 17.5 | 45.1852 | 45.1852 | 45.1852

## Abstract
ABSTRACT
| No. of Projects | 61
| Ongoing | 48
| New | 13
| Allocation | 2850
| Ongoing | 2558.741
| New | 291.261
| Due for Completion | 17
| Ongoing | 15
| New | 2

## ADP 2021-22 KP
ADP KP
Home Sector ADP 2021-22
Local Alloc.
S.NO | ADP/ Scheme # | Sub- Sector | Project Name | Date of Commt. | Date of Completion | Total Cost | Exp. upto 30.06.2021 | Capital | Revenue | Release | Foreign Alloc. | Total Alloc. | Rev. Alloc. | Re-appr (+) | Re- appr (-) | Surr. To P&D & Finance | Release | Rev. Alloc. | Exp. in CFY 2021-22 | Surr. To P&D on 16.05.17 | Surr. Agnst Alloc. | Surr. To P&D on 20.06.17 | Remarks | Remarks | Surr. To Finance on 30.06.17
Ongoing Schemes HTA's
1 | 864/170331 | HTA | Establishment of Forensic Science Laboratory (FSL) at Peshawar (UNDP Assisted). (B) CDWP / / |  |  | 0.001 | 0 | 0.001 | 0 |  |  | 0.001 |  |  |  |  | 0 |  | 0 |  |  |  | PC-1 submitted by the consultant along with draft Role of bussiness is processed for approval. Meeting on FSL is scheduled on 14.10-2021.
2 | 865/180093 | HTA | Reformation & Skills Development facilities for Probationers. (Rule of Law Roadmap) (A) DDWP 02/01/20 |  |  | 76.297 | 0 | 0 | 20 |  |  | 20 |  |  |  |  | 20 |  | 0 |  |  |  | ongoing scheme. Recruitment under process
3 | 866/180104 | HTA | Case Management & Monitoring System in the Prosecution Directorate and its District formation Offices. (Rule of Law Roadmap) (A) DDWP 01/08/19 |  |  | 94.927 | 0 | 0 | 40.393 |  |  | 40.393 |  |  |  |  | 40.393 |  | 0 |  |  |  | Revised PC-I amounting to Rs 134.010 submitted to P&DD.Department. Revenue clearance granted by FD
4 | 867/180518 | HTA | Computerization of Arms Licenses in the remaining Districts of Khyber Pakhtunkhwa. (A) DDWP 06/11/19 |  |  | 50.976 | 0.983 | 0 | 15 |  |  | 15 |  |  |  |  | 15 |  | 0 |  |  |  | ongoing scheme . Recruitment under process
5 | 868/200089 | HTA | Establishment & Strengthening of Civilian oversight Bodies under Khyber Pakhtunkhwa Police Act, 2017 (A) DDWP 13/10/20 |  |  | 100 | 1.869 | 0 | 50 |  |  | 50 |  |  |  |  | 50 |  | 2.943 |  |  |  | ongoing scheme. Procuremnt under process
6 | 869/210316 | HTA | Acquisition of Land for Construction of Forensic Science Laboratory in Peshawar PDWP 25-02.201 |  |  | 320 | 0 | 67.816 | 0 |  |  | 67.816 |  |  |  |  | 67.816 |  | 0 |  |  |  | On the direction of CM KP, a committee will be constituted U/C of Secretary Local Govt to fix the rate for acquisition of 40 kanal land.
| Total |  |  | 0 | 0 | 642.201 | 2.852 | 67.817 | 125.393 | 0 | 0 | 193.21 | 0 | 0 | 0 | 0 | 193.209 |  | 2.943
New Schemes HTA's
7 | 870/160435 | HTA | Strengthening Rule of Law Project (SRLP) (UNDP Assisted). PDWP cleared on 31.01.2018. (B) CDWP / / |  |  | 800 | 0 | 0 | 0.001 |  |  | 0.001 | [6 empty] | 0 |  |  |  | Agreement signed with UNDP. |  | 0
8 | 871/210237 | HTA | Missing Facilites in the newly Constructed Khyber Pakhtunkhwa Prosecution Training Academy |  |  | 68 | 0 | 0 | 12.601 |  |  | 12.601 | [6 empty] | 0 |  |  |  | PC-I of the Scheme has been approved at cost of Rs. 44.00 M.
9 | 872/210540 | HTA | Safe City Project, Swat |  |  | 150 | 0 | 0 | 1 |  |  | 1 | [6 empty] | 0 |  |  |  | PPO is requested to submit PC-I. Police Department informed that they are unable to execute the scheme.
| Total |  |  | 0 | 0 | 1018 | 0 | 0 | 13.602 | 0 | 0 | 13.602 | [6 empty] | 0 | [5 empty] | #REF!
Ongoing Schemes Police
10 | 873/020602 | Police | Construction of Central Police Office in Peshawar. (A) PDWP 23/12/16 |  |  | 658.83 | 542.19 | 91.548 | 0 |  |  | 91.548 |  |  |  |  | 91.548 |  | 0 |  |  |  | ongoing scheme
11 | 874/120248 | Police | Special Development Support for Khyber Pakhtunkhwa Police (Tor Ghar = Rs. 400.00 M) (SDSP Phase-III) (A) PDWP 07/08/2012 |  |  | 2000 | 1449.053 | 100 | 0 |  |  | 100 |  |  |  |  | 100 |  | 20.431 |  |  |  | ongoing scheme
12 | 875/130378 | Police | Special Development Support for Khyber Pakhtunkhwa Police. (SDSP-IV) (A) PDWP 29/01/15 |  |  | 1048 | 742.013 | 90 | 0 |  |  | 90 |  |  |  |  | 90 |  | 2.316 |  |  |  | ongoing scheme
13 | 876/140150 | Police | Establishment of Project Management Unit (PMU) for Safe City Project Peshawar. (A) PDWP 27/01/17 |  |  | 142.608 | 94.999 | 0 | 20 |  |  | 20 |  |  |  |  | 20 |  | 3.133 |  |  |  | ongoing scheme
14 | 877/140263 | Police | F/S & Construction of Headquarters for Counter Terrorism Department at District Peshawar (Ternab). (A) PDWP 11/03/16 |  |  | 231.573 | 164.024 | 74.604 | 0 |  |  | 74.604 |  |  |  |  | 74.604 | [5 empty] | ongoing scheme
15 | 878/140807 | Police | F/S and Development of Police Infrastructure in Khyber Pakhtunkhwa (Police Station Kabalgram, Chauga, Olandar, Dandai District Shangla, Swari at District Buner, Gawaleri and Gat- Poechar at District Swat, Kuz Paro District Kohistan (CM Directive) (A) PDWP 26/11/15 |  |  | 345 | 233.73 | 40 | 0 |  |  | 40 |  |  |  |  | 40 |  | 5.923 |  |  |  | ongoing scheme
16 | 879/160133 | Police | F/S and Strengthening of Police Infrastructure in Khyber Pakhtunkhwa. (A) PDWP 18/10/17 |  |  | 425.02 | 146.626 | 29.5 | 0 |  |  | 29.5 |  |  |  |  | 29.5 |  | 21.936 |  |  |  | ongoing scheme
17 | 880/160541 | Police | F/S and Construction of Bachlor Hostel of Police at Police Lines Peshawar. (A) PDWP 16/02/17 |  |  | 218.536 | 172.546 | 46.011 | 0 |  |  | 46.011 |  |  |  |  | 46.011 | [5 empty] | ongoing scheme
18 | 881/160542 | Police | F/S and Construction of Model Police Station at each Tehsil & Town Headquarter of Khyber Pakhtunkhwa (13 No.s). PDWP 27/07/17 |  |  | 1107.41 | 373.412 | 140 | 0 |  |  | 140 |  |  |  |  | 140 |  | 85.542 |  |  |  | ongoing scheme
19 | 882/160544 | Police | F/S and Construction of Regional Headquarters for Counter Terrorism. (A) PDWP 27/07/17 |  |  | 660.594 | 332.062 | 70 | 0 |  |  | 70 |  |  |  |  | 70 |  | 58.681 |  |  |  | ongoing scheme
20 | 883/190142 | Police | E-Enablement of Special Branch Phase-II. DDWP 24/12/20 |  |  | 92.74 | 0 | 0 | 20 |  |  | 20 |  |  |  |  | 20 |  | 0 |  |  |  | ongoing scheme
21 | 884/190432 | Police | Refurbishment of Existing Police Stations. (A) PDWP 18/02/20 |  |  | 145.215 | 0 | 40 | 0 |  |  | 40 |  |  |  |  | 40 |  | 0 |  |  |  | ongoing scheme
22 | 885/200033 | Police | Acquisition of Land for Heavy Firing Range adjacent to Elite Police Training Center, Nowshera (A) PDWP 19/03/20 |  |  | 203.033 | 30.606 | 30 | 0 |  |  | 30 |  |  |  |  | 30 |  | 30 |  |  |  | ongoing scheme
23 | 886/200123 | Police | F/S & Construction of Police Stations and Police Posts in Malakand Division. (B) DDWP 24/12/20 |  |  | 1348.315 | 0 | 40 | 0 |  |  | 40 |  |  |  |  | 40 |  | 0 |  |  |  | Revenue Clearance has been issued by FD and AA has also been issued at a cost of 1348.315 by the Competent Auhtority. Payment for acquisition of land is inprocess. Enhancement of allocation of the scheme for CFY 2021-22 is still awaited.
24 | 887/200162 | Police | Establishment of Police Post at Tehkal Peshawar (A) DDWP 24/12/20 |  |  | 25 | 0 | 5 | 0 |  |  | 5 |  |  |  |  | 5 |  | 0 |  |  |  | Land not yet identified by the Police Department.
| Total |  |  | 0 | 0 | 8651.874 | 4281.261 | 796.663 | 40 | 0 | 0 | 836.663 | 0 | 0 | 0 | 0 | 836.663 | 0 | [6 empty] | #REF!
New Schemes Police
25 | 888/210035 | Police | Purchase of land for construction of Police Lines Shangla |  |  | 75.22 | 0 | 75.22 | 0 |  |  | 75.22 | [6 empty] | 0 |  |  |  | The scheme is completed. Payment has been made to DC Shangla for further disbursement to Land owner. |  | 0
26 | 889/210037 | Police | Construction of Police Station Jani Khel Bannu |  |  | 100 | 0 | 2.8 | 0 |  |  | 2.8 | [6 empty] | 0 |  |  |  | Scheme is single sourced to Pak Army. DDWP forum approved the scheme on 25.08.2021.
27 | 890/210038 | Police | Purchase of land for access road to joint Police training center (JPTC) Hakim Abad Nowshera |  |  | 16.194 | 0 | 3.239 | 0 |  |  | 3.239 | [6 empty] | 0 |  |  |  | Scheme has been approved during the DDWP meeting held on 25.08.2021 accordingly A.A issued.
28 | 891/210541 | Police | Construction of Auditorium at Police Training College, Hangu |  |  | 90 | 0 | 2 | 0 |  |  | 2 | [6 empty] | 0 |  |  |  | PC-II of the scheme is presented before the DDWP forum wherein the forum directed to submit PC-I.
29 | 892/210542 | Police | Construction /Re-Construction and Rehabilitation of Police Stations in Khyber Pakhtunkhwa |  |  | 1350 | 0 | 60 | 0 |  |  | 60 | [6 empty] | 0 |  |  |  | PC-II amounting to 67.00 M of the scheme is forwarded to P&DD.
| Total |  |  | 0 | 0 | 1631.414 | 0 | 143.259 | 0 | 0 | 0 | 143.259
Ongoing Schemes Prisons
30 | 893/110131 | Prison | Improvement of Existing Jails in Khyber Pakhtunkhwa. (A) PDWP 23/12/16 |  |  | 410.019 | 356.923 | 20 | 0 |  |  | 20 |  |  |  |  | 20 | [5 empty] | Pre-PDWP held on the revised PC-I, observations forwarded to Prison Department for rectification. |  | 0
31 | 894/120189 | Prison | Construction of District Jail Swabi (Phase-II). (A) PDWP 16/11/17 |  |  | 1398 | 323 | 223 | 0 |  |  | 223 |  |  |  |  | 223 |  | 0 |  |  |  | ongoing scheme
32 | 895/140132 | Prison | Re-Construction of District Jail Swat. (A) PDWP 03/11 /16 |  |  | 707 | 660.683 | 72.597 | 0 |  |  | 72.597 |  |  |  |  | 72.597 |  | 20.61 |  |  |  | Revised PC-I has been submitted to P&DD amounting to Rs. 813 M. Pre PDWP held minutes forwarde to prison department for rectification
33 | 896/140205 | Prison | F/S & Construction of Admin Blocks and Barracks for Prison Security Force (Watch & ward Staff) in Khyber Pakhtunkhwa. (A) PDWP 03/11 /16 |  |  | 450.7 | 327.607 | 46.057 | 0 |  |  | 46.057 |  |  |  |  | 46.057 |  | 17.209 |  |  |  | ongoing scheme
34 | 897/150272 | Prison | Feasibility Study and Construction of Central Prison D.I.Khan on existing site (Phase-II). (A) PDWP 10/03/16 |  |  | 812.996 | 289.011 | 35.4 | 0 |  |  | 35.4 |  |  |  |  | 35.4 |  | 10.697 |  |  |  | ongoing scheme
35 | 898/170041 | Prison | Establishment of Planning and Monitoring Cell at Inspectorate General of Prisons, KP. (B) DDWP 18/04/18 |  |  | 31.606 | 25.932 | 0 | 10 |  |  | 10 |  |  |  |  | 10 |  | 0.0679 |  |  |  | ongoing scheme
36 | 899/180090 | Prison | Feasibility Study for Prison Industries and skill Development of Prisoners ( Rule of Law road map) DDWP 13/10/2020 |  |  | 51.972 | 1.272 | 23.6 | 0 |  |  | 23.6 |  |  |  |  | 23.6 |  | 0 |  |  |  | ongoing scheme. Recruitment under process
37 | 900/200032 | Prison | Security Enhancement of Central Prison, Mardan |  |  | 68.813 | 4.988 | 68.812 | 0 |  |  | 68.812 |  |  |  |  | 68.812 |  | 0 |  |  |  | ongoing scheme
38 | 901/170039 | Prison | Feasibilty study, Planning Designing and Construction of Central Prison Peshawar (Phase-II) |  |  | 3206.45 | 0 | 35.4 | 0 |  |  | 35.4 |  |  |  |  | 0 |  | 0 |  |  |  | PC-II approved Prision department is requested to submit PC-1
| Total |  |  | 0 | 0 | 7137.556 | 1989.416 | 524.866 | 10 | 0 | 0 | 534.866 | 0 | 0 | 0 | 0 | 499.466
New Schemes Prisons
39 | 902/210394 | Prison | Conectivity of NAB Courts, NAB Detention cells and Prisons through Video link |  |  | 7 | 0 | 0 | 1.4 |  |  | 1.4 | [6 empty] | 0 |  |  |  | PC-I forwarded for DDWP approval.
| Total |  |  | 0 | 0 | 7 | 0 | 0 | 1.4 | 0 | 0 | 1.4 | [11 empty] | % Against Rev. Alloc. | #REF!
| G.Total |  |  | 0 | 0 | 19088.045 | 6273.529 | 1532.605 | 190.395 | 0 | 0 | 1723 | [9 empty] | 0 |  | #REF! | #REF!
| Non-ADP | Police | Acquisition of Land for Access Road to Joint Police Training Centre Nowshera. (A) PDWP 21/12/2017 |  |  | 11.818 |  |  |  | 0 | 0 | 0 |  | 4.274 | 0 | 0 | 0 | 4.274 | 0 |  |  |  | PC-I amounting to Rs.11.818 (M) approved in the PDWP meting held on 21.12.2017.
#DIV/0!
#REF!

## ADP 2021-22 NMD
ADP Merged Areas
Home Sector ADP 2020-21
Local Alloc.
S.No | ADP/ Scheme # | Sub- Sector | Project Name | Date of Commt. | Total Cost | Exp. upto 30.06.2020 | Capital | Revenue | Release | Total Alloc. | Rev. Alloc. | Re-appr (+) | Re- appr (-) | Release | Exp. in CFY 2020-21 | Surr. To P&D on 16.05.17 | Surr. Agnst Alloc. | Surr. To P&D on 20.06.17 | Remarks | Remarks | Surr. To Finance on 30.06.17
Ongoing Schemes HTA's
1 | 903/191586 | HTA | De-Radicalization/ Re-habilitation Center in Tribal Districts [MA]. (180582) |  | 566.778 | 547.304 | 0 | 38.474 |  | 38.474 |  |  |  | 38.474 | 0 |  |  |  | Revenue clearance of both the components received. Pre PDWP held. PC-I resubmitted for PDWP approval
2 | 904/191588 | HTA | 030435 - Creation of Crises Management Cell in FATA Secretariat. |  | 135.435 | 130.637 | 0 | 12.248 |  | 12.248 |  |  |  | 12.248 | 2.844 |  |  |  | Ongoing Scheme
| Total |  |  | 0 | 702.213 | 677.941 | 0 | 50.722 | 0 | 50.722 | 0 | 0 | 0 | 50.722 | 2.844 | 0 | 0
New Schemes HTA's
3 | 905/210040 | HTA | Computerization of Arms Licenses in the newly Merged Districts. |  | 140 | 0 | 0 | 50 |  | 50 |  |  |  |  | 0 |  |  |  | SO arms is requested to submit PC-I.
4 | 906/210315 | HTA | Construction of Yadgaar e Wafa Monument at Landikotal District Khyber |  | 25 | 0 | 25 | 0 |  | 25 |  |  |  |  | 0 |  |  |  | DG PCU requested DPO Khyber to submit PC-I.
| Total |  |  | 0 | 165 | 0 | 25 | 50 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ongoing Schemes Police
5 | 907/191115 | Police | M&R/Establishment of Check Posts and Barracks for Levies/Khassadars in SWA [MA] |  | 79.441 |  | 0.001 | 0 |  | 0.001 |  |  |  |  | 0 |  |  |  | 13- Units, Work in progress
6 | 908/191118 | Police | Construction /Re-construction and Rehabilitation of Levy Check Posts /Picquets in FR Peshawar. [MA] (170200) |  | 26.06 | 12.755 | 15.305 | 0 |  | 15.305 |  |  |  | 15.305 | 0 |  |  |  | 11 total site. Work on 08 sites is in progress. While sites for 03 units is not clear. AC is requested for site clearance
7 | 909/191120 | Police | M&R / Construction of Levies Picquets in NWA. [MA] (170174) |  | 40.994 | 35.158 | 6.51 | 0 |  | 6.51 |  |  |  | 6.51 | 0 |  |  |  | Total 10- components. 2 Nos picquets completed. Work on 05 Nos units in progress. Site dispute on 03 Nos picquets |  | 0
8 | 910/191134 | Police | Reconstruction of 24 Nos. Levy Picquets from Khajori to Miranshah in NWA. (Revised) [MA] (140384) |  | 159.12 | 145.039 | 14.084 | 0 |  | 14.084 |  |  |  | 14.084 | 0 |  |  |  | Total 35 units. 18 Units completed, 13 Remaining in progress. 04 units cannot be completed due to site dispute.
9 | 911/191136 | Police | Construction of Levies Picquets in District North Waziristan. [MA] (180340) |  | 45.021 | 19.021 | 18.744 | 0 |  | 18.744 |  |  |  | 18.744 | 0 |  |  |  | Total 10- components. 2 Nos picquets completed and waiting for H/O. 05 Nos work in progress. Work on 03 Nos picquets stopped due to dispute on sites
10 | 912/191139 | Police | Construction of small Levy /Khassadar Head Quarter at Paya Jawaki Sub-Division Kohat. [MA] (180464 |  | 17 | 0 | 17 | 0 |  | 17 |  |  |  | 17 | 0 |  |  |  | During the previous FY, Police Department Kohat directed to submit PC-I for the scheme but till date no PC-I was submitted to this Department inspite of telephonic request again and again. The Police Department seemed that they do not own the scheme.
11 | 913/191516 | Police | Construction of Levies/Khasaadars Barracks & Levy Line in District South Waziristan [MA] |  | 30.043 |  | 0.001 | 0 |  | 0.001 |  |  |  |  | 0 |  |  |  | 02- Units 1- Main building upto DPC level, Bore completed. 2- Roof level.
12 | 914/191179 | Police | Construction and Rehabilitation of Levy Barracks, Levy Picquets and Lockups in All Agencies /FRs. [MA] (170342) |  | 396.548 | 171.21 | 66.964 | 0 |  | 66.964 |  |  |  | 66.964 | 0 |  |  |  | work on 9 different places on various units is an progress
13 | 915/191587 | Police | Establishment of Levy Training Center at Shah Kass, Khyber Agency. [MA] (100205) |  | 173.12 | 131.558 | 0 | 24.671 |  | 24.671 |  |  |  | 24.671 | 3.672 |  |  |  | Ongoing Scheme
| Total |  |  | 0 | 887.906 | 514.741 | 138.608 | 24.671 | 0 | 163.279 | 0 | 0 | 0 | 163.278 | 3.672 | 0 | 0 |  |  |  | #REF!
#REF!
#REF!

## AIP 2021-22
ADP AIP Sector
Home Sector ADP 2020-21
Local Alloc.
| ADP/ Scheme # | Sub- Sector | Project Name | Date of Commt. | Total Cost | Exp. upto 30.06.2020 | Capital | Revenue | Release | Foreign Alloc. | Total Alloc. | Rev. Alloc. | Re-appr (+) | Re- appr (-) | Surr. To P&D & Finance | Release | Exp. in CFY 2020-21 | Surr. To P&D on 16.05.17 | Surr. Agnst Alloc. | Surr. To P&D on 20.06.17 | Remarks | Remarks | Surr. To Finance on 30.06.17
Ongoing Schemes HTA's
1 | 916/195240 | HTA | Extension of Prosecution Services in the Newly Merged Districts Erstwhile FATA (AIP). (A) PDWP 08/10/19 |  | 126.704 | 14.845 | 0 | 20 |  |  | 20 |  |  |  |  | 20 |  |  |  |  | ongoing scheme.
2 | 917/195241 | HTA | Extension of Parole and Probation Services in the Newly Merged Districts Erstwhile FATA (AIP). (A) PDWP 08/10/19 |  | 47.125 | 0.882 | 0 | 20 |  |  | 20 |  |  |  |  | 20 |  |  |  |  | ongoing scheme.
| Total |  |  | 0 | 173.829 | 15.727 | 0 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0
Ongoing Schemes Police
3 | 918/195238 | Police | F/S & Construction of Police Stations and Police Posts including levies transformations (Police/DG PCU) (AIP) (A) PDWP 08/10/19 |  | 7191.99 | 1.572 | 500 | 0 |  |  | 500 |  |  |  |  | 500 | 71.827 |  |  |  | Ongoing scheme.
4 | 919/195239 | Police | Training Programs for Police and Levies alongwith necessary equipments (Police/D.I.G Training) (AIP) (A) PDWP 08/10/19 |  | 1267.727 | 1128.784 | 0 | 100 |  |  | 100 |  |  |  |  | 100 | 100 |  |  |  | scheme under revision. Revised PC-1 submitted to F.D. Meeting held in F.D for revenue clearance. |  | 0
5 | 920/210042 | Police | Strenghening of Counter Terrorism Department in Newly Mergd Districts |  | 112 | 0 | 0 | 20 |  |  | 20 |  |  |  |  | 20 | 0 |  |  |  | Scheme approved with revised cost of Rs. 844.00 M. Summary for enhanced cost & revise revenue clearance is under process as per direction of PDWP forum.
| Total |  |  | 0 | 8571.717 | 1130.356 | 500 | 120 | 0 | 0 | 620 | 0 | 0 | 0 | 0 | 620 | 171.827 | 0 | 0 |  |  |  | #REF!
New Schemes Police
6 | 921/210041 | Police | Establishment of Police Lines at Miran Shah, North Waziristan |  | 796.73 | 0 | 50 | 0 |  |  | 50 | [5 empty] | 0 |  |  |  | Scheme single sourced to Pak-Army. Pre-PDWP held reply of the observation submitted to P&DD.
7 | 922/210202 | Police | Security of Khyber Spinal Route |  | 120 | 0 | 0 | 8 |  |  | 8 | [5 empty] | 0 |  |  |  | DG PCU submitted PC-I which is forwarded to F.D for revenue clearance.
| Total |  |  | 0 | 916.73 | 0 | 50 | 8 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ongoing Schemes Prison
8 | 923/195237 | Prison | Improvement of Existing Political Lockups (Sub Jail) and Providing Arms & Ammunitions along with other necessary Equipments (AIP) |  | 817.59 | 201.629 | 100 | 0 |  |  | 100 |  |  |  |  | 100 | 0 |  |  |  | ongoing scheme
9 | 924/200088 | Prison | F/S for Construction of District Jails in Merged Districts (AIP) |  | 20 | 0 | 20 | 0 |  |  | 20 |  |  |  |  | 20 | 1.92 |  |  |  | Revised PC-I amounting to Rs. 420.00 M submitted to P&DD, as directed for approval.
| Total |  |  | 0 | 837.59 | 201.629 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 1.92 | 0 | 0 |  |  |  | #REF!